## Blank Template
SAMPLE: Faculty 6 Month Review TIMELINE
Student Name: |  | Faculty: MNHS
Student ID: |  | School:
Date: |  | Main Supervisor:
* Student must indicate in the timeline below when milestones will be completed.
TIME FRAME FOR TASK COMPLETION
|  |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
Candidature Requirements | Thesis Task |  | Task Comments | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1
Compulsory MDP Modules | Monash Graduate Research Induction (online); Research Integrity (online); Faculty Induction (moodle) |  | To be completed within 30 days of commencement by all Graduate Research students | bar: Year 1 Q1
Milestones |  |  |  | Year 1 Q2: Initial; Year 1 Q4: Confirmation; Year 2 Q4: Progress Review; Year 3 Q4: Final Review
LEGEND
Compulsory MDP Modules
Candidature Milestones

## MNHS Example
SAMPLE: Faculty 6 Month Review TIMELINE
Student Name: |  | Faculty: MNHS
Student ID: |  | School:
Date: |  | Main Supervisor:
* Student must indicate in the timeline below when milestones will be completed.
TIME FRAME FOR TASK COMPLETION
|  |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
Candidature Requirements | Thesis Task |  | Task Comments | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1
Compulsory MDP Modules | Monash Graduate Research Induction (online); Research Integrity (online); Faculty Induction (moodle) |  | To be completed within 30 days of commencement by all Graduate Research students | bar: Year 1 Q1
Literature Review | bar: Year 1 Q1 to Year 1 Q2
Ethics clearance | bar: Year 1 Q1 to Year 1 Q2
LabArchives set-up | bar: Year 1 Q1
STUDY 1 | Data collection & analysis | bar: Year 1 Q3 to Year 2 Q1
Writing | bar: Year 2 Q1 to Year 2 Q3
STUDY 2 | Data collection & analysis | bar: Year 2 Q3 to Year 2 Q4
Writing | bar: Year 2 Q4 to Year 3 Q1
STUDY 3 | Data collection & analysis | bar: Year 3 Q1 to Year 3 Q2
Writing | bar: Year 3 Q3 to Year 3 Q4
FINAL THESIS WRITE-UP | bar: Year 3 Q4 to Year 4 Q1
Milestones |  |  |  | Year 1 Q2: Initial; Year 1 Q4: Confirmation; Year 2 Q4: Progress Review; Year 3 Q4: Final Review
LEGEND
Compulsory MDP Modules
Thesis Tasks
Candidature Milestones